## DigiLocker Threat Model
Severity | Likelihood | Impact | STRIDE | Function | CWE | Risk Category | Technical Asset | Communication Link | RAA % | Identified Risk | Action | Mitigation | Check | ID | Status | Justification | Date | Checked by | Ticket
High | Very Likely | High | Tampering | Development | CWE-89 | SQL/NoSQL-Injection | authentication-service | Auth Service to Database | 100 | SQL/NoSQL-Injection risk at authentication-service against database database via Auth Service to Database | SQL/NoSQL-Injection Prevention | Try to use parameter binding to be safe from injection vulnerabilities. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | sql-nosql-injection@authentication-service@database@authentication-service>auth-service-to-database | Unchecked
High | Very Likely | High | Tampering | Development | CWE-89 | SQL/NoSQL-Injection | consent-manager | Consent Manager to Database | 16 | SQL/NoSQL-Injection risk at consent-manager against database database via Consent Manager to Database | SQL/NoSQL-Injection Prevention | Try to use parameter binding to be safe from injection vulnerabilities. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | sql-nosql-injection@consent-manager@database@consent-manager>consent-manager-to-database | Unchecked
High | Very Likely | High | Tampering | Development | CWE-89 | SQL/NoSQL-Injection | digilocker-backend | Backend to Database | 85 | SQL/NoSQL-Injection risk at digilocker-backend against database database via Backend to Database | SQL/NoSQL-Injection Prevention | Try to use parameter binding to be safe from injection vulnerabilities. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | sql-nosql-injection@digilocker-backend@database@digilocker-backend>backend-to-database | Unchecked
High | Very Likely | High | Tampering | Development | CWE-89 | SQL/NoSQL-Injection | digilocker-backend | Backend to Document Repository | 85 | SQL/NoSQL-Injection risk at digilocker-backend against database document-repository via Backend to Document Repository | SQL/NoSQL-Injection Prevention | Try to use parameter binding to be safe from injection vulnerabilities. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | sql-nosql-injection@digilocker-backend@document-repository@digilocker-backend>backend-to-document-repository | Unchecked
High | Very Likely | High | Tampering | Development | CWE-89 | SQL/NoSQL-Injection | monitoring-service | Monitoring Service to Database | 1 | SQL/NoSQL-Injection risk at monitoring-service against database database via Monitoring Service to Database | SQL/NoSQL-Injection Prevention | Try to use parameter binding to be safe from injection vulnerabilities. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | sql-nosql-injection@monitoring-service@database@monitoring-service>monitoring-service-to-database | Unchecked
Elevated | Very Likely | Medium | Spoofing | Development | CWE-352 | Cross-Site Request Forgery (CSRF) | authentication-service | Gateway to Authentication Service | 100 | Cross-Site Request Forgery (CSRF) risk at authentication-service via Gateway to Authentication Service from api-gateway | CSRF Prevention | Try to use anti-CSRF tokens ot the double-submit patterns (at least for logged-in requests). When your authentication scheme depends on cookies (like session or token cookies), consider marking them with the same-site flag. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | cross-site-request-forgery@authentication-service@api-gateway>gateway-to-authentication-service | Unchecked
Elevated | Very Likely | Medium | Spoofing | Development | CWE-352 | Cross-Site Request Forgery (CSRF) | consent-manager | Backend to Consent Manager | 16 | Cross-Site Request Forgery (CSRF) risk at consent-manager via Backend to Consent Manager from digilocker-backend | CSRF Prevention | Try to use anti-CSRF tokens ot the double-submit patterns (at least for logged-in requests). When your authentication scheme depends on cookies (like session or token cookies), consider marking them with the same-site flag. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | cross-site-request-forgery@consent-manager@digilocker-backend>backend-to-consent-manager | Unchecked
Elevated | Very Likely | Medium | Spoofing | Development | CWE-352 | Cross-Site Request Forgery (CSRF) | digilocker-backend | Gateway to DigiLocker Backend | 85 | Cross-Site Request Forgery (CSRF) risk at digilocker-backend via Gateway to DigiLocker Backend from api-gateway | CSRF Prevention | Try to use anti-CSRF tokens ot the double-submit patterns (at least for logged-in requests). When your authentication scheme depends on cookies (like session or token cookies), consider marking them with the same-site flag. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | cross-site-request-forgery@digilocker-backend@api-gateway>gateway-to-digilocker-backend | Unchecked
Elevated | Very Likely | Medium | Spoofing | Development | CWE-352 | Cross-Site Request Forgery (CSRF) | identity-provider | Auth Service to Aadhaar Identity Provider | 35 | Cross-Site Request Forgery (CSRF) risk at identity-provider via Auth Service to Aadhaar Identity Provider from authentication-service | CSRF Prevention | Try to use anti-CSRF tokens ot the double-submit patterns (at least for logged-in requests). When your authentication scheme depends on cookies (like session or token cookies), consider marking them with the same-site flag. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | cross-site-request-forgery@identity-provider@authentication-service>auth-service-to-aadhaar-identity-provider | Unchecked
Elevated | Likely | High | Tampering | Development | CWE-79 | Cross-Site Scripting (XSS) | authentication-service |  | 100 | Cross-Site Scripting (XSS) risk at authentication-service | XSS Prevention | Try to encode all values sent back to the browser and also handle DOM-manipulations in a safe way to avoid DOM-based XSS. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | cross-site-scripting@authentication-service | Unchecked
Elevated | Likely | High | Tampering | Development | CWE-79 | Cross-Site Scripting (XSS) | citizen-web-portal |  | 26 | Cross-Site Scripting (XSS) risk at citizen-web-portal | XSS Prevention | Try to encode all values sent back to the browser and also handle DOM-manipulations in a safe way to avoid DOM-based XSS. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | cross-site-scripting@citizen-web-portal | Unchecked
Elevated | Likely | High | Tampering | Development | CWE-79 | Cross-Site Scripting (XSS) | consent-manager |  | 16 | Cross-Site Scripting (XSS) risk at consent-manager | XSS Prevention | Try to encode all values sent back to the browser and also handle DOM-manipulations in a safe way to avoid DOM-based XSS. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | cross-site-scripting@consent-manager | Unchecked
Elevated | Likely | High | Tampering | Development | CWE-79 | Cross-Site Scripting (XSS) | digilocker-backend |  | 85 | Cross-Site Scripting (XSS) risk at digilocker-backend | XSS Prevention | Try to encode all values sent back to the browser and also handle DOM-manipulations in a safe way to avoid DOM-based XSS. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | cross-site-scripting@digilocker-backend | Unchecked
Elevated | Likely | High | Tampering | Development | CWE-79 | Cross-Site Scripting (XSS) | identity-provider |  | 35 | Cross-Site Scripting (XSS) risk at identity-provider | XSS Prevention | Try to encode all values sent back to the browser and also handle DOM-manipulations in a safe way to avoid DOM-based XSS. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | cross-site-scripting@identity-provider | Unchecked
Elevated | Unlikely | Very High | Tampering | Operations | CWE-1008 | Missing Cloud Hardening |  |  | 0 | Missing Cloud Hardening risk at DMZ | Cloud Hardening | Apply hardening of all cloud components and services, taking special care to follow the individual risk descriptions (which depend on the cloud provider tags in the model). <br><br>For <b>Amazon Web Services (AWS)</b>: Follow the <i>CIS Benchmark for Amazon Web Services</i> (see also the automated checks of cloud audit tools like <i>"PacBot", "CloudSploit", "CloudMapper", "ScoutSuite", or "Prowler AWS CIS Benchmark Tool"</i>). <br>For EC2 and other servers running Amazon Linux, follow the <i>CIS Benchmark for Amazon Linux</i> and switch to IMDSv2. <br>For S3 buckets follow the <i>Security Best Practices for Amazon S3</i> at <a href="https://docs.aws.amazon.com/AmazonS3/latest/dev/security-best-practices.html">https://docs.aws.amazon.com/AmazonS3/latest/dev/security-best-practices.html</a> to avoid accidental leakage. <br>Also take a look at some of these tools: <a href="https://github.com/toniblyx/my-arsenal-of-aws-security-tools">https://github.com/toniblyx/my-arsenal-of-aws-security-tools</a> <br><br>For <b>Microsoft Azure</b>: Follow the <i>CIS Benchmark for Microsoft Azure</i> (see also the automated checks of cloud audit tools like <i>"CloudSploit" or "ScoutSuite"</i>).<br><br>For <b>Google Cloud Platform</b>: Follow the <i>CIS Benchmark for Google Cloud Computing Platform</i> (see also the automated checks of cloud audit tools like <i>"CloudSploit" or "ScoutSuite"</i>). <br><br>For <b>Oracle Cloud Platform</b>: Follow the hardening best practices (see also the automated checks of cloud audit tools like <i>"CloudSploit"</i>). | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-cloud-hardening@dmz | Unchecked
Elevated | Likely | Medium | Tampering | Operations | CWE-16 | Missing Hardening | authentication-service |  | 100 | Missing Hardening risk at authentication-service | System Hardening | Try to apply all hardening best practices (like CIS benchmarks, OWASP recommendations, vendor recommendations, DevSec Hardening Framework, DBSAT for Oracle databases, and others). | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-hardening@authentication-service | Unchecked
Elevated | Likely | Medium | Tampering | Operations | CWE-16 | Missing Hardening | database |  | 60 | Missing Hardening risk at database | System Hardening | Try to apply all hardening best practices (like CIS benchmarks, OWASP recommendations, vendor recommendations, DevSec Hardening Framework, DBSAT for Oracle databases, and others). | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-hardening@database | Unchecked
Elevated | Likely | Medium | Tampering | Operations | CWE-16 | Missing Hardening | digilocker-backend |  | 85 | Missing Hardening risk at digilocker-backend | System Hardening | Try to apply all hardening best practices (like CIS benchmarks, OWASP recommendations, vendor recommendations, DevSec Hardening Framework, DBSAT for Oracle databases, and others). | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-hardening@digilocker-backend | Unchecked
Elevated | Unlikely | Very High | Elevation of Privilege | Operations | CWE-1008 | Missing Identity Provider Isolation | authentication-service |  | 100 | Missing Identity Provider Isolation to further encapsulate and protect identity-related asset authentication-service against unrelated lower protected assets in the same network segment, which might be easier to compromise by attackers | Network Segmentation | Apply a network segmentation trust-boundary around the highly sensitive identity provider assets and their identity datastores. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-identity-provider-isolation@authentication-service | Unchecked
Elevated | Unlikely | Very High | Elevation of Privilege | Operations | CWE-1008 | Missing Identity Provider Isolation | identity-provider |  | 35 | Missing Identity Provider Isolation to further encapsulate and protect identity-related asset identity-provider against unrelated lower protected assets in the same network segment, which might be easier to compromise by attackers | Network Segmentation | Apply a network segmentation trust-boundary around the highly sensitive identity provider assets and their identity datastores. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-identity-provider-isolation@identity-provider | Unchecked
Elevated | Likely | Medium | Information Disclosure | Development | CWE-918 | Server-Side Request Forgery (SSRF) | api-gateway | Gateway to Authentication Service | 46 | Server-Side Request Forgery (SSRF) risk at api-gateway server-side web-requesting the target authentication-service via Gateway to Authentication Service | SSRF Prevention | Try to avoid constructing the outgoing target URL with caller controllable values. Alternatively use a mapping (whitelist) when accessing outgoing URLs instead of creating them including caller controllable values. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | server-side-request-forgery@api-gateway@authentication-service@api-gateway>gateway-to-authentication-service | Unchecked
Elevated | Likely | Medium | Information Disclosure | Development | CWE-918 | Server-Side Request Forgery (SSRF) | api-gateway | Gateway to DigiLocker Backend | 46 | Server-Side Request Forgery (SSRF) risk at api-gateway server-side web-requesting the target digilocker-backend via Gateway to DigiLocker Backend | SSRF Prevention | Try to avoid constructing the outgoing target URL with caller controllable values. Alternatively use a mapping (whitelist) when accessing outgoing URLs instead of creating them including caller controllable values. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | server-side-request-forgery@api-gateway@digilocker-backend@api-gateway>gateway-to-digilocker-backend | Unchecked
Elevated | Likely | Medium | Information Disclosure | Development | CWE-918 | Server-Side Request Forgery (SSRF) | authentication-service | Auth Service to Aadhaar Identity Provider | 100 | Server-Side Request Forgery (SSRF) risk at authentication-service server-side web-requesting the target identity-provider via Auth Service to Aadhaar Identity Provider | SSRF Prevention | Try to avoid constructing the outgoing target URL with caller controllable values. Alternatively use a mapping (whitelist) when accessing outgoing URLs instead of creating them including caller controllable values. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | server-side-request-forgery@authentication-service@identity-provider@authentication-service>auth-service-to-aadhaar-identity-provider | Unchecked
Elevated | Likely | Medium | Information Disclosure | Development | CWE-918 | Server-Side Request Forgery (SSRF) | citizen-web-portal | Web Portal to API Gateway | 26 | Server-Side Request Forgery (SSRF) risk at citizen-web-portal server-side web-requesting the target api-gateway via Web Portal to API Gateway | SSRF Prevention | Try to avoid constructing the outgoing target URL with caller controllable values. Alternatively use a mapping (whitelist) when accessing outgoing URLs instead of creating them including caller controllable values. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | server-side-request-forgery@citizen-web-portal@api-gateway@citizen-web-portal>web-portal-to-api-gateway | Unchecked
Elevated | Likely | Medium | Information Disclosure | Development | CWE-918 | Server-Side Request Forgery (SSRF) | digilocker-backend | Backend to Consent Manager | 85 | Server-Side Request Forgery (SSRF) risk at digilocker-backend server-side web-requesting the target consent-manager via Backend to Consent Manager | SSRF Prevention | Try to avoid constructing the outgoing target URL with caller controllable values. Alternatively use a mapping (whitelist) when accessing outgoing URLs instead of creating them including caller controllable values. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | server-side-request-forgery@digilocker-backend@consent-manager@digilocker-backend>backend-to-consent-manager | Unchecked
Elevated | Likely | Medium | Information Disclosure | Development | CWE-918 | Server-Side Request Forgery (SSRF) | digilocker-backend | Backend to Issuer Service | 85 | Server-Side Request Forgery (SSRF) risk at digilocker-backend server-side web-requesting the target issuer-service via Backend to Issuer Service | SSRF Prevention | Try to avoid constructing the outgoing target URL with caller controllable values. Alternatively use a mapping (whitelist) when accessing outgoing URLs instead of creating them including caller controllable values. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | server-side-request-forgery@digilocker-backend@issuer-service@digilocker-backend>backend-to-issuer-service | Unchecked
Elevated | Likely | Medium | Information Disclosure | Development | CWE-918 | Server-Side Request Forgery (SSRF) | digilocker-backend | Backend to Monitoring Service | 85 | Server-Side Request Forgery (SSRF) risk at digilocker-backend server-side web-requesting the target monitoring-service via Backend to Monitoring Service | SSRF Prevention | Try to avoid constructing the outgoing target URL with caller controllable values. Alternatively use a mapping (whitelist) when accessing outgoing URLs instead of creating them including caller controllable values. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | server-side-request-forgery@digilocker-backend@monitoring-service@digilocker-backend>backend-to-monitoring-service | Unchecked
Elevated | Likely | Medium | Information Disclosure | Development | CWE-918 | Server-Side Request Forgery (SSRF) | digilocker-backend | Backend to Notification Service | 85 | Server-Side Request Forgery (SSRF) risk at digilocker-backend server-side web-requesting the target notification-service via Backend to Notification Service | SSRF Prevention | Try to avoid constructing the outgoing target URL with caller controllable values. Alternatively use a mapping (whitelist) when accessing outgoing URLs instead of creating them including caller controllable values. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | server-side-request-forgery@digilocker-backend@notification-service@digilocker-backend>backend-to-notification-service | Unchecked
Elevated | Likely | Medium | Information Disclosure | Development | CWE-918 | Server-Side Request Forgery (SSRF) | digilocker-backend | Backend to Requester Service | 85 | Server-Side Request Forgery (SSRF) risk at digilocker-backend server-side web-requesting the target requester-service via Backend to Requester Service | SSRF Prevention | Try to avoid constructing the outgoing target URL with caller controllable values. Alternatively use a mapping (whitelist) when accessing outgoing URLs instead of creating them including caller controllable values. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | server-side-request-forgery@digilocker-backend@requester-service@digilocker-backend>backend-to-requester-service | Unchecked
Elevated | Very Likely | Medium | Elevation of Privilege | Architecture | CWE-501 | Unguarded Access From Internet | api-gateway | Web Portal to API Gateway | 46 | Unguarded Access from Internet of api-gateway by citizen-web-portal via Web Portal to API Gateway | Encapsulation of Technical Asset | Encapsulate the asset behind a guarding service, application, or reverse-proxy. For admin maintenance a bastion-host should be used as a jump-server. For file transfer a store-and-forward-host should be used as an indirect file exchange platform. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unguarded-access-from-internet@api-gateway@citizen-web-portal@citizen-web-portal>web-portal-to-api-gateway | Unchecked
Elevated | Very Likely | Medium | Elevation of Privilege | Architecture | CWE-501 | Unguarded Access From Internet | api-gateway | Mobile App to API Gateway | 46 | Unguarded Access from Internet of api-gateway by mobile-app via Mobile App to API Gateway | Encapsulation of Technical Asset | Encapsulate the asset behind a guarding service, application, or reverse-proxy. For admin maintenance a bastion-host should be used as a jump-server. For file transfer a store-and-forward-host should be used as an indirect file exchange platform. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unguarded-access-from-internet@api-gateway@mobile-app@mobile-app>mobile-app-to-api-gateway | Unchecked
Elevated | Very Likely | Medium | Elevation of Privilege | Architecture | CWE-501 | Unguarded Access From Internet | authentication-service | Gateway to Authentication Service | 100 | Unguarded Access from Internet of authentication-service by api-gateway via Gateway to Authentication Service | Encapsulation of Technical Asset | Encapsulate the asset behind a guarding service, application, or reverse-proxy. For admin maintenance a bastion-host should be used as a jump-server. For file transfer a store-and-forward-host should be used as an indirect file exchange platform. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unguarded-access-from-internet@authentication-service@api-gateway@api-gateway>gateway-to-authentication-service | Unchecked
Elevated | Very Likely | Medium | Elevation of Privilege | Architecture | CWE-501 | Unguarded Access From Internet | digilocker-backend | Gateway to DigiLocker Backend | 85 | Unguarded Access from Internet of digilocker-backend by api-gateway via Gateway to DigiLocker Backend | Encapsulation of Technical Asset | Encapsulate the asset behind a guarding service, application, or reverse-proxy. For admin maintenance a bastion-host should be used as a jump-server. For file transfer a store-and-forward-host should be used as an indirect file exchange platform. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unguarded-access-from-internet@digilocker-backend@api-gateway@api-gateway>gateway-to-digilocker-backend | Unchecked
Elevated | Likely | Medium | Elevation of Privilege | Architecture | CWE-501 | Unguarded Direct Datastore Access | database | Auth Service to Database | 60 | Unguarded Direct Datastore Access of database by authentication-service via Auth Service to Database | Encapsulation of Datastore | Encapsulate the datastore access behind a guarding service or application. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unguarded-direct-datastore-access@authentication-service>auth-service-to-database@authentication-service@database | Unchecked
Elevated | Likely | Medium | Elevation of Privilege | Architecture | CWE-501 | Unguarded Direct Datastore Access | database | Consent Manager to Database | 60 | Unguarded Direct Datastore Access of database by consent-manager via Consent Manager to Database | Encapsulation of Datastore | Encapsulate the datastore access behind a guarding service or application. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unguarded-direct-datastore-access@consent-manager>consent-manager-to-database@consent-manager@database | Unchecked
Elevated | Likely | Medium | Elevation of Privilege | Architecture | CWE-501 | Unguarded Direct Datastore Access | database | Backend to Database | 60 | Unguarded Direct Datastore Access of database by digilocker-backend via Backend to Database | Encapsulation of Datastore | Encapsulate the datastore access behind a guarding service or application. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unguarded-direct-datastore-access@digilocker-backend>backend-to-database@digilocker-backend@database | Unchecked
Elevated | Likely | Medium | Elevation of Privilege | Architecture | CWE-501 | Unguarded Direct Datastore Access | database | Monitoring Service to Database | 60 | Unguarded Direct Datastore Access of database by monitoring-service via Monitoring Service to Database | Encapsulation of Datastore | Encapsulate the datastore access behind a guarding service or application. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unguarded-direct-datastore-access@monitoring-service>monitoring-service-to-database@monitoring-service@database | Unchecked
Elevated | Likely | Medium | Elevation of Privilege | Architecture | CWE-501 | Unguarded Direct Datastore Access | document-repository | Backend to Document Repository | 33 | Unguarded Direct Datastore Access of document-repository by digilocker-backend via Backend to Document Repository | Encapsulation of Datastore | Encapsulate the datastore access behind a guarding service or application. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unguarded-direct-datastore-access@digilocker-backend>backend-to-document-repository@digilocker-backend@document-repository | Unchecked
Medium | Unlikely | High | Tampering | Operations | CWE-912 | Container Base Image Backdooring | api-gateway |  | 46 | Container Base Image Backdooring risk at api-gateway | Container Infrastructure Hardening | Apply hardening of all container infrastructures (see for example the <i>CIS-Benchmarks for Docker and Kubernetes</i> and the <i>Docker Bench for Security</i>). Use only trusted base images of the original vendors, verify digital signatures and apply image creation best practices. Also consider using Google's <i>Distroless</i> base images or otherwise very small base images. Regularly execute container image scans with tools checking the layers for vulnerable components. | Are recommendations from the linked cheat sheet and referenced ASVS/CSVS applied? | container-baseimage-backdooring@api-gateway | Unchecked
Medium | Unlikely | High | Tampering | Operations | CWE-912 | Container Base Image Backdooring | authentication-service |  | 100 | Container Base Image Backdooring risk at authentication-service | Container Infrastructure Hardening | Apply hardening of all container infrastructures (see for example the <i>CIS-Benchmarks for Docker and Kubernetes</i> and the <i>Docker Bench for Security</i>). Use only trusted base images of the original vendors, verify digital signatures and apply image creation best practices. Also consider using Google's <i>Distroless</i> base images or otherwise very small base images. Regularly execute container image scans with tools checking the layers for vulnerable components. | Are recommendations from the linked cheat sheet and referenced ASVS/CSVS applied? | container-baseimage-backdooring@authentication-service | Unchecked
Medium | Unlikely | High | Tampering | Operations | CWE-912 | Container Base Image Backdooring | consent-manager |  | 16 | Container Base Image Backdooring risk at consent-manager | Container Infrastructure Hardening | Apply hardening of all container infrastructures (see for example the <i>CIS-Benchmarks for Docker and Kubernetes</i> and the <i>Docker Bench for Security</i>). Use only trusted base images of the original vendors, verify digital signatures and apply image creation best practices. Also consider using Google's <i>Distroless</i> base images or otherwise very small base images. Regularly execute container image scans with tools checking the layers for vulnerable components. | Are recommendations from the linked cheat sheet and referenced ASVS/CSVS applied? | container-baseimage-backdooring@consent-manager | Unchecked
Medium | Unlikely | High | Tampering | Operations | CWE-912 | Container Base Image Backdooring | digilocker-backend |  | 85 | Container Base Image Backdooring risk at digilocker-backend | Container Infrastructure Hardening | Apply hardening of all container infrastructures (see for example the <i>CIS-Benchmarks for Docker and Kubernetes</i> and the <i>Docker Bench for Security</i>). Use only trusted base images of the original vendors, verify digital signatures and apply image creation best practices. Also consider using Google's <i>Distroless</i> base images or otherwise very small base images. Regularly execute container image scans with tools checking the layers for vulnerable components. | Are recommendations from the linked cheat sheet and referenced ASVS/CSVS applied? | container-baseimage-backdooring@digilocker-backend | Unchecked
Medium | Unlikely | High | Tampering | Operations | CWE-912 | Container Base Image Backdooring | monitoring-service |  | 1 | Container Base Image Backdooring risk at monitoring-service | Container Infrastructure Hardening | Apply hardening of all container infrastructures (see for example the <i>CIS-Benchmarks for Docker and Kubernetes</i> and the <i>Docker Bench for Security</i>). Use only trusted base images of the original vendors, verify digital signatures and apply image creation best practices. Also consider using Google's <i>Distroless</i> base images or otherwise very small base images. Regularly execute container image scans with tools checking the layers for vulnerable components. | Are recommendations from the linked cheat sheet and referenced ASVS/CSVS applied? | container-baseimage-backdooring@monitoring-service | Unchecked
Medium | Unlikely | Medium | Tampering | Operations | CWE-912 | Container Base Image Backdooring | notification-service |  | 5 | Container Base Image Backdooring risk at notification-service | Container Infrastructure Hardening | Apply hardening of all container infrastructures (see for example the <i>CIS-Benchmarks for Docker and Kubernetes</i> and the <i>Docker Bench for Security</i>). Use only trusted base images of the original vendors, verify digital signatures and apply image creation best practices. Also consider using Google's <i>Distroless</i> base images or otherwise very small base images. Regularly execute container image scans with tools checking the layers for vulnerable components. | Are recommendations from the linked cheat sheet and referenced ASVS/CSVS applied? | container-baseimage-backdooring@notification-service | Unchecked
Medium | Unlikely | Medium | Tampering | Architecture | CWE-1127 | Missing Build Infrastructure | authentication-service |  | 100 | Missing Build Infrastructure in the threat model (referencing asset authentication-service as an example) | Build Pipeline Hardening | Include the build infrastructure in the model. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-build-infrastructure@authentication-service | Unchecked
Medium | Unlikely | Medium | Elevation of Privilege | Architecture | CWE-284 | Missing Identity Propagation | consent-manager | Backend to Consent Manager | 16 | Missing Enduser Identity Propagation over communication link Backend to Consent Manager from digilocker-backend to consent-manager | Identity Propagation and Resource-based Authorization | When processing requests for endusers if possible authorize in the backend against the propagated identity of the enduser. This can be achieved in passing JWTs or similar tokens and checking them in the backend services. For DevOps usages apply at least a technical-user authorization. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-identity-propagation@digilocker-backend>backend-to-consent-manager@digilocker-backend@consent-manager | Unchecked
Medium | Unlikely | Medium | Elevation of Privilege | Architecture | CWE-284 | Missing Identity Propagation | issuer-service | Backend to Issuer Service | 16 | Missing Enduser Identity Propagation over communication link Backend to Issuer Service from digilocker-backend to issuer-service | Identity Propagation and Resource-based Authorization | When processing requests for endusers if possible authorize in the backend against the propagated identity of the enduser. This can be achieved in passing JWTs or similar tokens and checking them in the backend services. For DevOps usages apply at least a technical-user authorization. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-identity-propagation@digilocker-backend>backend-to-issuer-service@digilocker-backend@issuer-service | Unchecked
Medium | Unlikely | Medium | Elevation of Privilege | Architecture | CWE-284 | Missing Identity Propagation | requester-service | Backend to Requester Service | 9 | Missing Enduser Identity Propagation over communication link Backend to Requester Service from digilocker-backend to requester-service | Identity Propagation and Resource-based Authorization | When processing requests for endusers if possible authorize in the backend against the propagated identity of the enduser. This can be achieved in passing JWTs or similar tokens and checking them in the backend services. For DevOps usages apply at least a technical-user authorization. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-identity-propagation@digilocker-backend>backend-to-requester-service@digilocker-backend@requester-service | Unchecked
Medium | Unlikely | Medium | Spoofing | Architecture | CWE-287 | Missing Identity Store | digilocker-backend |  | 85 | Missing Identity Store in the threat model (referencing asset digilocker-backend as an example) | Identity Store | Include an identity store in the model if the application has a login. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-identity-store@digilocker-backend | Unchecked
Medium | Unlikely | Medium | Elevation of Privilege | Operations | CWE-1008 | Missing Network Segmentation | authentication-service |  | 100 | Missing Network Segmentation to further encapsulate and protect authentication-service against unrelated lower protected assets in the same network segment, which might be easier to compromise by attackers | Network Segmentation | Apply a network segmentation trust-boundary around the highly sensitive assets and/or datastores. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-network-segmentation@authentication-service | Unchecked
Medium | Unlikely | Medium | Elevation of Privilege | Business Side | CWE-308 | Missing Two-Factor Authentication (2FA) | api-gateway | Mobile App to API Gateway | 46 | Missing Two-Factor Authentication covering communication link Mobile App to API Gateway from mobile-app to api-gateway | Authentication with Second Factor (2FA) | Apply an authentication method to the technical asset protecting highly sensitive data via two-factor authentication for human users. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-authentication-second-factor@mobile-app>mobile-app-to-api-gateway@mobile-app@api-gateway | Unchecked
Medium | Unlikely | Medium | Elevation of Privilege | Business Side | CWE-308 | Missing Two-Factor Authentication (2FA) | api-gateway | Web Portal to API Gateway | 46 | Missing Two-Factor Authentication covering communication link Web Portal to API Gateway from citizen-web-portal to api-gateway | Authentication with Second Factor (2FA) | Apply an authentication method to the technical asset protecting highly sensitive data via two-factor authentication for human users. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-authentication-second-factor@citizen-web-portal>web-portal-to-api-gateway@citizen-web-portal@api-gateway | Unchecked
Medium | Unlikely | Medium | Information Disclosure | Architecture | CWE-522 | Missing Vault (Secret Storage) | authentication-service |  | 100 | Missing Vault (Secret Storage) in the threat model (referencing asset authentication-service as an example) | Vault (Secret Storage) | Consider using a Vault (Secret Storage) to securely store and access config secrets (like credentials, private keys, client certificates, etc.). | Is a Vault (Secret Storage) in place? | missing-vault@authentication-service | Unchecked
Medium | Unlikely | Medium | Tampering | Operations | CWE-1008 | Missing Web Application Firewall (WAF) | authentication-service |  | 100 | Missing Web Application Firewall (WAF) risk at authentication-service | Web Application Firewall (WAF) | Consider placing a Web Application Firewall (WAF) in front of the web-services and/or web-applications. For cloud environments many cloud providers offer pre-configured WAFs. Even reverse proxies can be enhances by a WAF component via ModSecurity plugins. | Is a Web Application Firewall (WAF) in place? | missing-waf@authentication-service | Unchecked
Medium | Unlikely | Medium | Tampering | Operations | CWE-1008 | Missing Web Application Firewall (WAF) | digilocker-backend |  | 85 | Missing Web Application Firewall (WAF) risk at digilocker-backend | Web Application Firewall (WAF) | Consider placing a Web Application Firewall (WAF) in front of the web-services and/or web-applications. For cloud environments many cloud providers offer pre-configured WAFs. Even reverse proxies can be enhances by a WAF component via ModSecurity plugins. | Is a Web Application Firewall (WAF) in place? | missing-waf@digilocker-backend | Unchecked
Medium | Unlikely | Medium | Tampering | Operations | CWE-1008 | Missing Web Application Firewall (WAF) | identity-provider |  | 35 | Missing Web Application Firewall (WAF) risk at identity-provider | Web Application Firewall (WAF) | Consider placing a Web Application Firewall (WAF) in front of the web-services and/or web-applications. For cloud environments many cloud providers offer pre-configured WAFs. Even reverse proxies can be enhances by a WAF component via ModSecurity plugins. | Is a Web Application Firewall (WAF) in place? | missing-waf@identity-provider | Unchecked
Medium | Unlikely | Medium | Tampering | Operations | CWE-1008 | Missing Web Application Firewall (WAF) | issuer-service |  | 16 | Missing Web Application Firewall (WAF) risk at issuer-service | Web Application Firewall (WAF) | Consider placing a Web Application Firewall (WAF) in front of the web-services and/or web-applications. For cloud environments many cloud providers offer pre-configured WAFs. Even reverse proxies can be enhances by a WAF component via ModSecurity plugins. | Is a Web Application Firewall (WAF) in place? | missing-waf@issuer-service | Unchecked
Medium | Unlikely | Medium | Tampering | Operations | CWE-1008 | Missing Web Application Firewall (WAF) | requester-service |  | 9 | Missing Web Application Firewall (WAF) risk at requester-service | Web Application Firewall (WAF) | Consider placing a Web Application Firewall (WAF) in front of the web-services and/or web-applications. For cloud environments many cloud providers offer pre-configured WAFs. Even reverse proxies can be enhances by a WAF component via ModSecurity plugins. | Is a Web Application Firewall (WAF) in place? | missing-waf@requester-service | Unchecked
Medium | Unlikely | Medium | Information Disclosure | Operations | CWE-311 | Unencrypted Technical Assets | database |  | 60 | Unencrypted Technical Asset named database missing enduser-individual encryption with data-with-enduser-individual-key | Encryption of Technical Asset | Apply encryption to the technical asset. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unencrypted-asset@database | Unchecked
Medium | Unlikely | Medium | Information Disclosure | Operations | CWE-311 | Unencrypted Technical Assets | document-repository |  | 33 | Unencrypted Technical Asset named document-repository missing enduser-individual encryption with data-with-enduser-individual-key | Encryption of Technical Asset | Apply encryption to the technical asset. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unencrypted-asset@document-repository | Unchecked
Medium | Unlikely | Medium | Elevation of Privilege | Architecture | CWE-1008 | Unnecessary Data Transfer | api-gateway |  | 46 | Unnecessary Data Transfer of consent-records data at api-gateway from/to digilocker-backend | Attack Surface Reduction | Try to avoid sending or receiving sensitive data assets which are not required (i.e. neither processed or stored) by the involved technical asset. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unnecessary-data-transfer@consent-records@api-gateway@digilocker-backend | Unchecked
Medium | Unlikely | Medium | Elevation of Privilege | Architecture | CWE-1008 | Unnecessary Data Transfer | digilocker-backend |  | 85 | Unnecessary Data Transfer of digital-signatures data at digilocker-backend from/to issuer-service | Attack Surface Reduction | Try to avoid sending or receiving sensitive data assets which are not required (i.e. neither processed or stored) by the involved technical asset. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unnecessary-data-transfer@digital-signatures@digilocker-backend@issuer-service | Unchecked
Medium | Unlikely | Medium | Elevation of Privilege | Architecture | CWE-1008 | Unnecessary Data Transfer | api-gateway |  | 46 | Unnecessary Data Transfer of issued-documents data at api-gateway from/to digilocker-backend | Attack Surface Reduction | Try to avoid sending or receiving sensitive data assets which are not required (i.e. neither processed or stored) by the involved technical asset. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unnecessary-data-transfer@issued-documents@api-gateway@digilocker-backend | Unchecked
Low | Unlikely | Low | Elevation of Privilege | Architecture | CWE-1008 | Unnecessary Data Transfer | api-gateway |  | 46 | Unnecessary Data Transfer of uploaded-documents data at api-gateway from/to digilocker-backend | Attack Surface Reduction | Try to avoid sending or receiving sensitive data assets which are not required (i.e. neither processed or stored) by the involved technical asset. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unnecessary-data-transfer@uploaded-documents@api-gateway@digilocker-backend | Unchecked
Low | Unlikely | Low | Denial of Service | Operations | CWE-400 | DoS-risky Access Across Trust-Boundary | api-gateway | Web Portal to API Gateway | 46 | Denial-of-Service risky access of api-gateway by citizen-web-portal via Web Portal to API Gateway | Anti-DoS Measures | Apply anti-DoS techniques like throttling and/or per-client load blocking with quotas. Also for maintenance access routes consider applying a VPN instead of public reachable interfaces. Generally applying redundancy on the targeted technical asset reduces the risk of DoS. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | dos-risky-access-across-trust-boundary@api-gateway@citizen-web-portal@citizen-web-portal>web-portal-to-api-gateway | Unchecked
Low | Unlikely | Low | Denial of Service | Operations | CWE-400 | DoS-risky Access Across Trust-Boundary | api-gateway | Mobile App to API Gateway | 46 | Denial-of-Service risky access of api-gateway by mobile-app via Mobile App to API Gateway | Anti-DoS Measures | Apply anti-DoS techniques like throttling and/or per-client load blocking with quotas. Also for maintenance access routes consider applying a VPN instead of public reachable interfaces. Generally applying redundancy on the targeted technical asset reduces the risk of DoS. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | dos-risky-access-across-trust-boundary@api-gateway@mobile-app@mobile-app>mobile-app-to-api-gateway | Unchecked
Low | Unlikely | Low | Denial of Service | Operations | CWE-400 | DoS-risky Access Across Trust-Boundary | authentication-service | Gateway to Authentication Service | 100 | Denial-of-Service risky access of authentication-service by api-gateway via Gateway to Authentication Service | Anti-DoS Measures | Apply anti-DoS techniques like throttling and/or per-client load blocking with quotas. Also for maintenance access routes consider applying a VPN instead of public reachable interfaces. Generally applying redundancy on the targeted technical asset reduces the risk of DoS. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | dos-risky-access-across-trust-boundary@authentication-service@api-gateway@api-gateway>gateway-to-authentication-service | Unchecked
Low | Unlikely | Low | Denial of Service | Operations | CWE-400 | DoS-risky Access Across Trust-Boundary | database | Auth Service to Database | 60 | Denial-of-Service risky access of database by authentication-service via Auth Service to Database | Anti-DoS Measures | Apply anti-DoS techniques like throttling and/or per-client load blocking with quotas. Also for maintenance access routes consider applying a VPN instead of public reachable interfaces. Generally applying redundancy on the targeted technical asset reduces the risk of DoS. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | dos-risky-access-across-trust-boundary@database@authentication-service@authentication-service>auth-service-to-database | Unchecked
Low | Unlikely | Low | Denial of Service | Operations | CWE-400 | DoS-risky Access Across Trust-Boundary | database | Consent Manager to Database | 60 | Denial-of-Service risky access of database by consent-manager via Consent Manager to Database | Anti-DoS Measures | Apply anti-DoS techniques like throttling and/or per-client load blocking with quotas. Also for maintenance access routes consider applying a VPN instead of public reachable interfaces. Generally applying redundancy on the targeted technical asset reduces the risk of DoS. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | dos-risky-access-across-trust-boundary@database@consent-manager@consent-manager>consent-manager-to-database | Unchecked
Low | Unlikely | Low | Denial of Service | Operations | CWE-400 | DoS-risky Access Across Trust-Boundary | database | Backend to Database | 60 | Denial-of-Service risky access of database by digilocker-backend via Backend to Database | Anti-DoS Measures | Apply anti-DoS techniques like throttling and/or per-client load blocking with quotas. Also for maintenance access routes consider applying a VPN instead of public reachable interfaces. Generally applying redundancy on the targeted technical asset reduces the risk of DoS. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | dos-risky-access-across-trust-boundary@database@digilocker-backend@digilocker-backend>backend-to-database | Unchecked
Low | Unlikely | Low | Denial of Service | Operations | CWE-400 | DoS-risky Access Across Trust-Boundary | database | Monitoring Service to Database | 60 | Denial-of-Service risky access of database by monitoring-service via Monitoring Service to Database | Anti-DoS Measures | Apply anti-DoS techniques like throttling and/or per-client load blocking with quotas. Also for maintenance access routes consider applying a VPN instead of public reachable interfaces. Generally applying redundancy on the targeted technical asset reduces the risk of DoS. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | dos-risky-access-across-trust-boundary@database@monitoring-service@monitoring-service>monitoring-service-to-database | Unchecked
Low | Unlikely | Low | Denial of Service | Operations | CWE-400 | DoS-risky Access Across Trust-Boundary | digilocker-backend | Gateway to DigiLocker Backend | 85 | Denial-of-Service risky access of digilocker-backend by api-gateway via Gateway to DigiLocker Backend | Anti-DoS Measures | Apply anti-DoS techniques like throttling and/or per-client load blocking with quotas. Also for maintenance access routes consider applying a VPN instead of public reachable interfaces. Generally applying redundancy on the targeted technical asset reduces the risk of DoS. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | dos-risky-access-across-trust-boundary@digilocker-backend@api-gateway@api-gateway>gateway-to-digilocker-backend | Unchecked
Low | Unlikely | Low | Denial of Service | Operations | CWE-400 | DoS-risky Access Across Trust-Boundary | document-repository | Backend to Document Repository | 33 | Denial-of-Service risky access of document-repository by digilocker-backend via Backend to Document Repository | Anti-DoS Measures | Apply anti-DoS techniques like throttling and/or per-client load blocking with quotas. Also for maintenance access routes consider applying a VPN instead of public reachable interfaces. Generally applying redundancy on the targeted technical asset reduces the risk of DoS. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | dos-risky-access-across-trust-boundary@document-repository@digilocker-backend@digilocker-backend>backend-to-document-repository | Unchecked
Low | Unlikely | Low | Denial of Service | Operations | CWE-400 | DoS-risky Access Across Trust-Boundary | identity-provider | Auth Service to Aadhaar Identity Provider | 35 | Denial-of-Service risky access of identity-provider by authentication-service via Auth Service to Aadhaar Identity Provider | Anti-DoS Measures | Apply anti-DoS techniques like throttling and/or per-client load blocking with quotas. Also for maintenance access routes consider applying a VPN instead of public reachable interfaces. Generally applying redundancy on the targeted technical asset reduces the risk of DoS. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | dos-risky-access-across-trust-boundary@identity-provider@authentication-service@authentication-service>auth-service-to-aadhaar-identity-provider | Unchecked